## tblProjects
ProjectID | ProjectName | Client | StartDate | EndDate | Status
P001 | Website Redesign | Client A | 2026-01-01 | 2026-03-31 | Active
P002 | Marketing Campaign | Client B | 2026-01-01 | 2026-03-31 | Active
P003 | Product Launch | Client C | 2026-01-01 | 2026-03-31 | Active

## tblTeam
Member | Role | CapacityHrsPerWeek
Amit | Analyst | 40
Ravi | Analyst | 40
Sneha | Analyst | 40
Neha | Analyst | 40
Kiran | Analyst | 40

## tblTasks
TaskID | ProjectID | Title | Assignee | CreatedDate | StartDate | DueDate | ClosedDate | Status | Priority | StoryPoints | IsClosed | Overdue | CycleTimeDays | LeadTimeDays
T1 | P001 | Task 1 | Sneha | 2026-01-31 | 2026-01-31 | 2026-02-09 | 2026-02-04 | Done | High | 6 | TRUE | FALSE | 4 | 4
T2 | P002 | Task 2 | Ravi | 2026-01-17 | 2026-01-20 | 2026-01-27 |  | To Do | Medium | 2 | FALSE | TRUE
T3 | P001 | Task 3 | Sneha | 2026-01-24 | 2026-01-27 | 2026-01-31 |  | To Do | Medium | 3 | FALSE | TRUE
T4 | P003 | Task 4 | Kiran | 2026-01-02 | 2026-01-04 | 2026-01-14 | 2026-01-05 | Done | Low | 2 | TRUE | FALSE | 1 | 3
T5 | P002 | Task 5 | Ravi | 2026-01-11 | 2026-01-12 | 2026-01-15 |  | To Do | Medium | 3 | FALSE | TRUE
T6 | P001 | Task 6 | Ravi | 2026-01-20 | 2026-01-21 | 2026-01-27 |  | Blocked | Medium | 4 | FALSE | TRUE
T7 | P003 | Task 7 | Kiran | 2026-01-14 | 2026-01-16 | 2026-01-26 |  | To Do | High | 5 | FALSE | TRUE
T8 | P003 | Task 8 | Neha | 2026-01-24 | 2026-01-27 | 2026-02-06 | 2026-02-02 | Done | Medium | 6 | TRUE | FALSE | 6 | 9
T9 | P003 | Task 9 | Sneha | 2026-01-25 | 2026-01-27 | 2026-02-04 | 2026-01-29 | Done | Low | 1 | TRUE | FALSE | 2 | 4
T10 | P002 | Task 10 | Amit | 2026-01-09 | 2026-01-09 | 2026-01-17 |  | In Progress | Medium | 1 | FALSE | TRUE
T11 | P001 | Task 11 | Sneha | 2026-01-21 | 2026-01-23 | 2026-01-26 | 2026-01-30 | Done | High | 6 | TRUE | FALSE | 7 | 9
T12 | P002 | Task 12 | Kiran | 2026-01-09 | 2026-01-12 | 2026-01-20 | 2026-01-13 | Done | High | 1 | TRUE | FALSE | 1 | 4
T13 | P002 | Task 13 | Amit | 2026-01-29 | 2026-01-29 | 2026-02-06 |  | In Progress | Medium | 1 | FALSE | TRUE
T14 | P003 | Task 14 | Ravi | 2026-01-17 | 2026-01-20 | 2026-01-30 | 2026-01-22 | Done | Medium | 6 | TRUE | FALSE | 2 | 5
T15 | P002 | Task 15 | Amit | 2026-01-13 | 2026-01-13 | 2026-01-22 |  | To Do | Medium | 6 | FALSE | TRUE
T16 | P001 | Task 16 | Ravi | 2026-01-31 | 2026-02-01 | 2026-02-04 |  | To Do | Low | 3 | FALSE | TRUE
T17 | P001 | Task 17 | Neha | 2026-01-13 | 2026-01-15 | 2026-01-19 | 2026-01-22 | Done | Low | 6 | TRUE | FALSE | 7 | 9
T18 | P003 | Task 18 | Sneha | 2026-01-14 | 2026-01-17 | 2026-01-25 |  | To Do | Low | 5 | FALSE | TRUE
T19 | P002 | Task 19 | Neha | 2026-01-25 | 2026-01-27 | 2026-02-01 |  | In Progress | Low | 3 | FALSE | TRUE
T20 | P002 | Task 20 | Neha | 2026-01-24 | 2026-01-24 | 2026-01-29 |  | To Do | Medium | 3 | FALSE | TRUE
T21 | P003 | Task 21 | Neha | 2026-01-10 | 2026-01-12 | 2026-01-16 |  | In Progress | Medium | 1 | FALSE | TRUE
T22 | P001 | Task 22 | Amit | 2026-01-31 | 2026-02-01 | 2026-02-08 |  | Blocked | Low | 5 | FALSE | TRUE
T23 | P002 | Task 23 | Kiran | 2026-01-22 | 2026-01-24 | 2026-02-03 |  | Blocked | Medium | 1 | FALSE | TRUE
T24 | P003 | Task 24 | Kiran | 2026-01-01 | 2026-01-02 | 2026-01-09 |  | In Progress | High | 3 | FALSE | TRUE
T25 | P003 | Task 25 | Kiran | 2026-01-17 | 2026-01-20 | 2026-01-24 |  | Blocked | Medium | 5 | FALSE | TRUE
T26 | P001 | Task 26 | Neha | 2026-01-26 | 2026-01-29 | 2026-02-08 |  | Blocked | High | 3 | FALSE | TRUE
T27 | P001 | Task 27 | Amit | 2026-01-28 | 2026-01-30 | 2026-02-09 |  | To Do | High | 4 | FALSE | TRUE
T28 | P002 | Task 28 | Amit | 2026-01-03 | 2026-01-03 | 2026-01-13 |  | To Do | Low | 7 | FALSE | TRUE
T29 | P001 | Task 29 | Amit | 2026-01-15 | 2026-01-15 | 2026-01-25 | 2026-01-16 | Done | Low | 5 | TRUE | FALSE | 1 | 1
T30 | P001 | Task 30 | Amit | 2026-01-01 | 2026-01-01 | 2026-01-06 |  | To Do | Medium | 7 | FALSE | TRUE
T31 | P001 | Task 31 | Amit | 2026-01-05 | 2026-01-08 | 2026-01-16 | 2026-01-15 | Done | Medium | 3 | TRUE | FALSE | 7 | 10
T32 | P001 | Task 32 | Kiran | 2026-01-26 | 2026-01-26 | 2026-02-05 |  | To Do | Medium | 8 | FALSE | TRUE
T33 | P001 | Task 33 | Sneha | 2026-01-17 | 2026-01-18 | 2026-01-26 |  | To Do | High | 6 | FALSE | TRUE
T34 | P001 | Task 34 | Amit | 2026-01-26 | 2026-01-27 | 2026-01-31 | 2026-02-01 | Done | High | 6 | TRUE | FALSE | 5 | 6
T35 | P002 | Task 35 | Sneha | 2026-01-15 | 2026-01-15 | 2026-01-22 | 2026-01-17 | Done | Low | 1 | TRUE | FALSE | 2 | 2
T36 | P002 | Task 36 | Sneha | 2026-01-26 | 2026-01-26 | 2026-02-01 | 2026-01-30 | Done | Medium | 3 | TRUE | FALSE | 4 | 4
T37 | P002 | Task 37 | Ravi | 2026-01-30 | 2026-02-02 | 2026-02-06 |  | In Progress | High | 8 | FALSE | TRUE
T38 | P001 | Task 38 | Amit | 2026-01-28 | 2026-01-29 | 2026-02-08 |  | Blocked | Low | 7 | FALSE | TRUE
T39 | P003 | Task 39 | Neha | 2026-01-27 | 2026-01-28 | 2026-02-01 | 2026-02-02 | Done | Low | 4 | TRUE | FALSE | 5 | 6
T40 | P001 | Task 40 | Amit | 2026-01-11 | 2026-01-14 | 2026-01-22 |  | In Progress | High | 5 | FALSE | TRUE
T41 | P003 | Task 41 | Neha | 2026-01-30 | 2026-02-02 | 2026-02-07 |  | In Progress | Low | 1 | FALSE | TRUE
T42 | P003 | Task 42 | Ravi | 2026-01-30 | 2026-02-01 | 2026-02-06 |  | In Progress | Low | 6 | FALSE | TRUE
T43 | P002 | Task 43 | Kiran | 2026-01-06 | 2026-01-09 | 2026-01-17 |  | To Do | Medium | 5 | FALSE | TRUE
T44 | P002 | Task 44 | Amit | 2026-01-20 | 2026-01-22 | 2026-01-28 |  | Blocked | Medium | 2 | FALSE | TRUE
T45 | P003 | Task 45 | Amit | 2026-01-29 | 2026-01-29 | 2026-02-02 |  | Blocked | High | 2 | FALSE | TRUE
T46 | P003 | Task 46 | Sneha | 2026-01-14 | 2026-01-15 | 2026-01-21 |  | Blocked | Low | 4 | FALSE | TRUE
T47 | P001 | Task 47 | Sneha | 2026-01-22 | 2026-01-24 | 2026-02-03 |  | In Progress | Low | 6 | FALSE | TRUE
T48 | P001 | Task 48 | Kiran | 2026-01-16 | 2026-01-18 | 2026-01-23 |  | Blocked | High | 5 | FALSE | TRUE
T49 | P003 | Task 49 | Sneha | 2026-01-28 | 2026-01-31 | 2026-02-08 | 2026-02-01 | Done | Low | 5 | TRUE | FALSE | 1 | 4
T50 | P003 | Task 50 | Amit | 2026-01-07 | 2026-01-10 | 2026-01-15 |  | Blocked | Low | 3 | FALSE | TRUE
Formulas:
Overdue = IF(AND([IsClosed]=FALSE,[DueDate]<TODAY()),TRUE,FALSE)

## tblTime
Date | TaskID | Member | Hours
2026-01-31 | T26 | Sneha | 7
2026-01-07 | T46 | Kiran | 8
2026-01-04 | T49 | Amit | 1
2026-01-11 | T2 | Amit | 4
2026-01-02 | T16 | Ravi | 6
2026-01-06 | T36 | Ravi | 8
2026-01-08 | T11 | Amit | 3
2026-01-01 | T39 | Neha | 8
2026-01-24 | T37 | Amit | 7
2026-01-17 | T48 | Neha | 6
2026-01-08 | T49 | Ravi | 2
2026-01-13 | T19 | Neha | 1
2026-01-11 | T14 | Kiran | 5
2026-01-03 | T31 | Sneha | 8
2026-01-10 | T33 | Kiran | 3
2026-01-07 | T29 | Sneha | 6
2026-01-13 | T38 | Ravi | 7
2026-01-16 | T36 | Sneha | 4
2026-01-18 | T39 | Kiran | 8
2026-01-08 | T50 | Kiran | 5
2026-01-30 | T37 | Ravi | 3
2026-01-22 | T45 | Amit | 8
2026-01-26 | T37 | Kiran | 7
2026-01-23 | T41 | Kiran | 6
2026-01-28 | T34 | Kiran | 6
2026-01-27 | T8 | Ravi | 5
2026-01-29 | T15 | Neha | 2
2026-01-20 | T4 | Amit | 8
2026-01-07 | T7 | Amit | 5
2026-01-16 | T21 | Sneha | 2
2026-01-29 | T40 | Ravi | 8
2026-01-20 | T18 | Amit | 5
2026-01-07 | T16 | Neha | 1
2026-01-07 | T47 | Ravi | 2
2026-01-21 | T36 | Ravi | 8
2026-01-03 | T5 | Kiran | 5
2026-01-09 | T8 | Amit | 1
2026-01-28 | T35 | Kiran | 5
2026-01-01 | T26 | Sneha | 1
2026-01-14 | T20 | Ravi | 5
2026-01-13 | T30 | Amit | 4
2026-01-08 | T46 | Ravi | 6
2026-01-05 | T44 | Neha | 3
2026-01-25 | T42 | Ravi | 3
2026-01-02 | T38 | Sneha | 4
2026-01-08 | T46 | Kiran | 3
2026-01-16 | T5 | Kiran | 7
2026-01-12 | T38 | Kiran | 4
2026-01-22 | T43 | Kiran | 7
2026-01-05 | T19 | Sneha | 7
2026-01-20 | T46 | Kiran | 2
2026-01-27 | T44 | Ravi | 1
2026-01-23 | T45 | Kiran | 3
2026-01-07 | T21 | Ravi | 6
2026-01-31 | T34 | Ravi | 1
2026-01-15 | T28 | Sneha | 6
2026-01-20 | T20 | Kiran | 7
2026-01-25 | T32 | Sneha | 6
2026-01-26 | T27 | Ravi | 8
2026-01-17 | T15 | Amit | 4
2026-01-10 | T18 | Amit | 7
2026-01-04 | T49 | Ravi | 2
2026-01-05 | T7 | Ravi | 7
2026-01-22 | T36 | Ravi | 6
2026-01-10 | T41 | Ravi | 5
2026-01-17 | T36 | Neha | 6
2026-01-05 | T29 | Ravi | 1
2026-01-16 | T17 | Neha | 6
2026-01-31 | T16 | Amit | 6
2026-01-28 | T33 | Kiran | 7
2026-01-23 | T30 | Amit | 5
2026-01-30 | T50 | Kiran | 6
2026-01-15 | T27 | Kiran | 7
2026-01-15 | T44 | Amit | 7
2026-01-04 | T30 | Sneha | 2
2026-01-06 | T10 | Ravi | 1
2026-01-26 | T44 | Sneha | 6
2026-01-29 | T18 | Amit | 4
2026-01-20 | T23 | Ravi | 6
2026-01-20 | T22 | Kiran | 6
2026-01-11 | T47 | Kiran | 3
2026-01-30 | T7 | Kiran | 1
2026-01-16 | T11 | Neha | 4
2026-01-23 | T41 | Kiran | 2
2026-01-24 | T36 | Kiran | 5
2026-01-26 | T39 | Amit | 5
2026-01-30 | T48 | Amit | 7
2026-01-15 | T32 | Sneha | 5
2026-01-18 | T35 | Ravi | 6
2026-01-07 | T27 | Amit | 6
2026-01-03 | T11 | Amit | 3
2026-01-16 | T3 | Amit | 6
2026-01-30 | T5 | Amit | 2
2026-01-23 | T12 | Ravi | 3
2026-01-01 | T1 | Amit | 3
2026-01-18 | T15 | Ravi | 5
2026-01-24 | T36 | Ravi | 6
2026-01-30 | T41 | Neha | 7
2026-01-11 | T32 | Amit | 4
2026-01-11 | T41 | Sneha | 8

## KPI_Summary
Metric | Value
Total Tasks | 50
Completed | 15
Pending | 10
Delayed | 35